Incident Action Plan

JULY 17th, 2015

SWAMPY

PARADISE COMPLEX

Wildfires SS027-15, SS028-15, SS036-15, SS073-15 (Swampy Lakes)

Wildfires SS037, SS065 (Paradise Gardens)

| # INCIDENT OBJECTIVES |  | . INCIDENT NAME |  |  | . DATE PREPARED | . TIME PREPARED |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Swampy Paradise Complex |  |  | July 16th, 2015 | 1800 |
| OPERATIONAL PERIOD (DATE/TIME) |  |  |  |  |  |  |
| July 17th, 2015 0900 - 2100 |  |  |  |  |  |  |
| GENERAL NOTE: This team is protecting the community of Hay River, the K’atlodeeche reserve and the sub-divisions of the Hay River corridor as well as managing the Swampy fire to ensure values in the area are not threatened. |  |  |  |  |  |  |
| GENERAL CONTROL OBJECTIVES FOR THE INCIDENT (INCLUDE ALTERNATIVES) OPS: Paradise Continue working the hotspots in Div A Widening and cleaning up contingency guard along the Hay River north of the fire, making wider where trees are tall Contingency is to do a burnout operation on the east side of hay river to eliminate the big stands of fuel and tie in to the existing fire, or do a black line but this is looking less likely as crews have a good handle on No Bucketing today, Crews continued working the line. Swampy Dozer work (tightline) completed and 2 Carter dozers demobed Thursday and returning to Paradise on Friday. Now working remaining hotspots along power line south of highway 6 Successful drip torch burn , cleaned up green finger along the old airport road where the spot fires were occurring Thursday, and Prepare for Ignition operation on the NE flank Friday (Daniel and Brent Together). Likely ready to hand back to region by in the next few days. Sustained action of #73 with ground crews working on getting tied in (14 type 1 fire fighters) - 95% Contained with expectation to call it UC on Friday. Completing the tightline around the northwest flank of the fire. |  |  |  |  |  |  |
| Weather: |  |  |  |  |  |  |
| Max Temp Min RH Wind Notes Paradise; 24; 38% (by 1900hrs); NW10G25-30 (1300hrs); NW10G20 by late afternoon. Swampy; 25; 40%; NW10G25; NW15G30 By peak burn. |
| GENERAL SAFETY MESSAGE |  |  |  |  |  |  |
| - Hotspots & Flare-ups are being safely suppressed. - Safety Zones and Escape Routes are well cut and flagged. - Please continue to do the same over the next few days. - It is calling for warmer and dryer today, be on the lookout for hot spots and flare-ups. - Swampy: poor comms at swampy – Lyle to check-in at HR-ENR 3 times/day at 876-874-8225 |  |  |  |  |  |  |
| PREPARED BY (PLANNING SECTION CHIEF) |  |  | APPROVED BY (INCIDENT COMMANDER) |  |  |  |
| Franco Nogarin |  |  | Daniel Allaire |  |  |  |

# Fire Behaviour Forecast for Paradise

# Fire Behaviour Forecast for Swampy

| # ASSIGNMENT LIST Paradise Dozer Group |  |  |  | Channel Frequency: 5 |  |  |  |  |  | 2. Division/Group Heavy Equipment |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name Swampy Paradise Complex |  |  |  | 4. Operational Period July 17 0900 - 2100 |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief | Edwin Gillis |  |  | Ignition |  |  |  |  |  |  |  |
| Dozer Boss | Manny Vital |  |  |  |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  | Leader |  |  | Number Persons | Trans. Needed | Notes |  |  |  |  |
| 9 dozers |  | Manny Vital |  |  |  |  |  |  |  |  |  |
| 7. Control Operations All 9 dozers are working form riverwood to paradise on the east side of the Hay river. Enterprise fire guard is now complete. |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by (Resource Unit Leader) |  |  | Approved by (Planning Section Chief) Franco Nogarin |  |  |  |  | Date prepared July 16th, 2015 |  |  | Time 1800 |

| # ASSIGNMENT LIST – Paradise Branch |  |  |  | Channel Frequency: 5 |  |  |  |  |  | 2. Division/Group Alpha/Bravo |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name Swampy Paradise Complex |  |  |  | 4. Operational Period July 17 0900-2100 |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief | Edwin Gillis |  |  | Ignition |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  | Leader |  |  | Number Persons | Trans. Needed | Notes |  |  |  |  |
| SS 10 |  | Lucas |  |  | 4 |  |  |  |  |  |  |
| ON 98 |  | Westby |  |  | 4 |  |  |  |  |  |  |
| ON 99 |  | Saville |  |  | 4 |  |  |  |  |  |  |
| ON 102 |  | Brignall |  |  | 4 |  |  |  |  |  |  |
| Paradise EFF #1 |  | Scott King |  |  | 5 |  |  |  |  |  |  |
| Paradise EFF #2 |  | Tyler |  |  | 5 |  |  |  |  |  |  |
| 7. Control Operations Focus on hotspots near H18. Crews working the line |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by (Resource Unit Leader) |  |  | Approved by (Planning Section Chief) Franco Nogarin |  |  |  |  | Date July 16th, 2015 |  |  | Time 1800 |

| # ASSIGNMENT LIST – Swampy Branch |  |  |  | Channel Frequency: 10 |  |  |  |  |  | 2. Division/Group |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name Swampy Paradise Complex |  |  |  | 4. Operational Period July 17 0900-2100 |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief | Edwin Gillis |  |  | Ignition |  |  |  |  |  |  |  |
| Branch Director | Lyle Froehlich |  |  | VPS |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  | Leader |  |  | Number Persons | Trans. Needed | Notes |  |  |  |  |
| SS 03 (SS028) |  |  |  |  | 5 |  | Crew assignments and names to be obtained from Lyle in the AM |  |  |  |  |
| Swampy EFF #1 (SS028) |  |  |  |  | 5 |  |  |  |  |  |  |
| SS 06 (SS073) |  |  |  |  | 5 |  |  |  |  |  |  |
| SS 02 (SS073) |  |  |  |  | 5 |  |  |  |  |  |  |
| ON 100 (SS073) |  |  |  |  | 5 |  |  |  |  |  |  |
| 7. Control Operations Crews will be assigned to work areas of concern as per the Branch Directors instructions |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by (Resource Unit Leader) |  |  | Approved by (Planning Section Chief) Franco Nogarin |  |  |  |  | Date July 16th, 2015 |  |  | Time 1800 |

| # SUMMARY OF CURRENT ACTIONS |  |  |
| --- | --- | --- |
| For period: Overview Objectives are still being met. Further Ignition will only be carried out as a contingency if the fire threatens values. Suppression of hotspots while the weather remains cooperative continues. Summary of Actions undertaken and results: Paradise - 9 Dozers continue to widen and cleaning up the guard From highway 5 – riverwood to SS037 - All of the values protection has been demobed with the exception of the Gravel Pit Cabin which will be demobed on Saturday - No Bucketing today, Crews have a good handle on this fire crews contoinue to work the line Swampy - Sustain suppression of fire SS073 - Ground crews and bucketing continue on last hostpots along the southern fire perimeter at power line - Ground ignition work Thursday went well to clean up green fingers of fuel on the old airport road where hotspots were occurring. - Tightline completed by Dozers, Dozers demobed back to Paradise. - . Consultation & Engagement: - IC Team Brief at 0800; Debrief w IC Team at 1800. - Brief at Paradise Garden with crew at 0900. - Distributed daily IAP to THR Fire Chief Potter at 0800. - Continue distributing daily IAP to appropriate personnel. - Distribute daily IAP to Regional Office & Warehouse. Posted daily for their information. - Transfer updated maps to cutouts & distribute/post. - Jordan Siurko filling in for information flow yesterday. - Tom Lakusta, FMD Manager to provide debrief on FMA to July 16. (Completed) Problems/Concerns: Hotspots are burning quite deep making them difficult to extinguish Observed Wx: At 1300 T21/24 RH50/76 Winds NNW5G18/WNW10G25 rain 0.8/0 for Paradise and Swampy respectively. |  |  |
| Time: 1800 | Date Prepared: July 16th, 2015 | Franco Nogarin |

| # MEDICAL PLAN |  |  | 1. INCIDENT NAME |  |  |  |  | 2 DATE PREPARED |  | 3. TIME PREPARED |  |  | 4. OPERATIONAL PERIOD |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Paradise Complex |  |  |  |  | July 16, 2015 |  | 1600 Hrs |  |  | July 17 0900-2100 |  |  |  |  |  |
| 5. INCIDENT MEDICAL AID STATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MEDICAL AID STATIONS |  |  |  |  |  | LOCATION |  |  |  |  |  |  |  |  |  |  | MEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| Hay River Hospital via Hay River Airport See workflow below… |  |  |  |  |  | Hay River |  |  |  |  |  |  |  |  |  |  | X |  |
| 6. TRANSPORTATION The medivac machine for Paradise is IUX, the medivac machine for Swampy is GKO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A. AMBULANCE SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  |  |  | ADDRESS |  |  |  |  |  |  |  | PHONE |  |  |  |  | PARAMEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| Hay River Ambulance |  |  |  | Hay River |  |  |  |  |  |  |  | 874-9333 |  |  |  |  | X |  |
| B. INCIDENT AMBULANCES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  |  |  | LOCATION |  |  |  |  |  |  |  |  |  |  |  |  | PARAMEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| **As Indicated Above |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. HOSPITALS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  | ADDRESS |  |  | TRAVEL TIME |  |  |  | PHONE |  |  |  |  | HELIPAD |  | BURN CENTER |  |  |
|  |  |  |  |  | AIR |  | GRND |  |  |  |  |  |  | YES | NO | YES |  | NO |
| Hay River Hospital |  | 3 Gaetz Drive |  |  |  |  | 30m |  | 867-874-7100 |  |  |  |  |  | X |  |  | X |
| Yellowknife Stanton Hosp. |  | Yellowknife |  |  |  |  |  |  | 867-920-7777 |  |  |  |  | X |  |  |  | X |
| Burn Unit |  | Edmonton |  |  |  |  |  |  |  |  |  |  |  | X |  | X |  |  |
| H.R.Hosp. Dir. Client Services – Sheryl Courtoreille (RN) |  |  |  |  |  |  |  |  | 867-874-7162 |  |  |  |  |  |  |  |  |  |
| 8. MEDICAL EMERGENCY PROCEDURES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Call hospital ahead of time and give # of injured, Nature of injuries and names if the injured. Incidents requiring medevac – Transport to the airport near main building. Hay river hospital will send emergency team to the airport to transport injured to HR Hospital – They request a crew member travel to the hospital to aid in answering questions. Give them ENR contact number of 867-874-8225. Info requested by Hospital on injured personnel: - Date of birth - Home Address - Next of Kin - Heath Card Info |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 206 ICS 8/78 | 9. PREPARED BY Franco Nogarin |  |  |  |  |  |  |  |  |  | 10. REVIEWED BY John Ongo |  |  |  |  |  |  |  |

# Incident Org Chart

| # INCIDENT COMMUNICATIONS PLAN |  |  | 1. INCIDENT NAME |  |  | 2. DATE/TIME PREPARED | 3. OPERATIONAL PERIOD DATE/TIME |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Paradise Complex |  |  | July 16th, 2000 | July 17th, 0900-2100 |  |
| Paradise Branch |  |  |  |  |  |  |  |  |
| Assigned to | FUNCTION | CHANNEL |  | Simplex/Duplex | REMARKS |  |  |
| All Crews | Ground Ops | 5 |  | 153.47 |  |  |  |
| Ignition | Ignition Operations | 14 |  | 161.535 | All aircraft should monitor 122.05 am |  |  |
| Swampy Branch |  |  |  |  |  |  |  |
| Swampy Branch | Ground Operations | 10 |  |  |  |  |  |
| Swampy Branch | Air Operations | 9 |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |
| 5. PREPARED BY Franco Nogarin |  |  |  |  |  |  |  |  |

# HELICOPTERS

Paradise

CALL SIGN		TYPE			MAKE		PILOT			Contract Ends

IUX			Intermediate		A-STAR	Jordan Hatch

SLY			Intermediate		350B-2	Felix Christians	July 18, 2015

Swampy

GKO			Intermediate		350B-2	Vern Brodhagen 	July 18, 2015

All Helicopters will continue to check in with XLI 55 for 30 minute check in

The medevac machine for Paradise is IUX

The medevac machine for Swampy is GKO

# MOB

| DATE | POSITION/TYPE | NAME | DESTINATION | TRANSPORT | Notes |
| --- | --- | --- | --- | --- | --- |
| July 17 | IC | Brent Starling | YHY | NWAL sched | Arrives ~0740 |
| July 17 | Info | Amber Simpson | YHY | Vehicle | Arrives ~1200 |

# NEW RESOURCE REQUEST

| RESOURCE NEED | DATE REQUIRED | DESTINATION | NOTES |
| --- | --- | --- | --- |

# OUTSTANDING ORDERS

| RESOURCE NEED | DATE REQUIRED | DATE REQUESTED | DESTINATION | NOTES |
| --- | --- | --- | --- | --- |

# DEMOB

| DATE | POSITION/TYPE | NAME | DESTINATION | TRANSPORT | Notes |
| --- | --- | --- | --- | --- | --- |
| July 17 | IC | Daniel | Fort Smith | ENR Truck |  |
| July 17 | Ops | Jules Fournel | Norman Wells | Rental |  |
| July 17 | ON98, ON 99, ON 100 & ON102 | With Arep Nick Edey | Ont | Charter | 42 Souls |
| July 17 | Information Officer | Frank McKay | Hay River | Personal Vehicle | Tribal groups down south. |
| July 23 | FBAN | Dustin Oikle | NS | Sched |  |
| July 23 | Ops | Edwin Gillis | PEI | Sched |  |
| July 23 | Safety | John Ongo | NS | Sched |  |
| July 24 | Fin/Adm | Emily M. | YFS |  |  |

SWAMPY PARADISE COMPLEX (SS-037) CONTACT INFORMATION

INCIDENT MANAGEMENT TEAM

Position	Name	Phone Number

IC	Brent Starling	(867) 872-0486

Plans	Franco Nogarin	(867) 872-0393

FBAN	Dustin Oikle	(902) 956-4125

Dozer Boss	Manny Vital	TBD

Ops	Edwin Gillis	(902) 432-2484

Swampy Branch Director	Lyle Froehlich	(867) 875-2504

Logistics	Daniel Lund	(867) 695-6676

Fin/Admin & Resource Unit	Emily McInnis-Wharton	(867) 444-8586

Fin/Admin & Time Unit	Raelene Lamalice	(867) 874-8225

Safety Officer	John Ongo	(902) 577-0930

Safety Officer	Jordyn Siurko	(867) 876-0601

Regional Office Duty Officer	Gerry Hordell	(867) 875-7443

District Area Office		(867) 875-5558

District Area Office Fire Clerk		(867) 875-5555

Incident Command Post	Raelene Lamalice	(867) 874-8225

Ontario A/Rep	Nick Edey	(807) 863-0026

Community Contacts

Mayor Andrew Cassidy	(867) 876-0528

Hay River Fire Chief, Ross Potter	(867) 876-0279

Hay River Ambulance Service	(867) 874-9333

Katl’odeeche First Nation Chief Roy Fabian	(867) 876-0079

Enterprise Mayor John Leskiw	(867) 984-3666

West Point First Nation	(867) 874-6677

Hay River Metis Council	(867) 874-4470

Dept. of Highways – Darin Murphy…………	(867) 875-7344

Dept. of Highways – Roy Norwegian	(867) 984-3421