Incident Action Plan

JULY 18th, 2015

SWAMPY

PARADISE COMPLEX

Wildfires SS027-15, SS028-15, SS036-15, SS073-15 (Swampy Lakes)

Wildfires SS037, SS065 (Paradise Gardens)

| # INCIDENT OBJECTIVES |  | . INCIDENT NAME |  |  | . DATE PREPARED | . TIME PREPARED |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Swampy Paradise Complex |  |  | July 17th, 2015 | 1800 |
| OPERATIONAL PERIOD (DATE/TIME) |  |  |  |  |  |  |
| July 18th, 2015 0900 - 2100 |  |  |  |  |  |  |
| GENERAL NOTE: This team is protecting the community of Hay River, the K’atlodeeche reserve and the sub-divisions of the Hay River corridor as well as managing the Swampy fire to ensure values in the area are not threatened. |  |  |  |  |  |  |
| GENERAL CONTROL OBJECTIVES FOR THE INCIDENT (INCLUDE ALTERNATIVES) OPS: Paradise Continue working the hotspots in Div A Dozers Demob Today. Demob Ontario Crews Today Continue work to complete the problem area near H18 Crews continue working the line with one hot spot left to complete. Demob the VAR (Gravel Pit Cabin) Complete sling pad to facilitate removal of equipment. Swampy working remaining hotspot to the east Ignition operation on the NE flank – weather permitting Likely ready to hand back to region by in the next few days. #73 UC. |  |  |  |  |  |  |
| Weather: |  |  |  |  |  |  |
| Max Temp Min RH Wind Notes Paradise; 24; 30-37%; S10G25; Switching to NW25G50 by 9pm. Swampy; 24; 30-37%; S10G25; Switching to NW25G50. |
| GENERAL SAFETY MESSAGE |  |  |  |  |  |  |
| - Hotspots & Flare-ups are being safely suppressed. - Safety Zones and Escape Routes are well cut and flagged. - Please continue to do the same over the next few days. - It is calling for warmer and dryer today, be on the lookout for hot spots and flare-ups. - Swampy: poor comms at swampy – Lyle to check-in at HR-ENR 3 times/day at 876-874-8225 |  |  |  |  |  |  |
| PREPARED BY (PLANNING SECTION CHIEF) |  |  | APPROVED BY (INCIDENT COMMANDER) |  |  |  |
| Franco Nogarin |  |  | Brent Starling |  |  |  |

# Fire Behaviour Forecast for Paradise

# Fire Behaviour Forecast for Swampy

| # ASSIGNMENT LIST Paradise Dozer Group |  |  |  | Channel Frequency: 5 |  |  |  |  |  | 2. Division/Group Heavy Equipment |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name Swampy Paradise Complex |  |  |  | 4. Operational Period July 18 0900 - 2100 |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief | Edwin Gillis |  |  | Ignition |  |  |  |  |  |  |  |
| Div Sup | Manny Vital |  |  |  |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  | Leader |  |  | Number Persons | Trans. Needed | Notes |  |  |  |  |
| 9 dozers |  | Manny Vital |  |  |  |  | Demob today – Remember to inform each operator that they are done today. |  |  |  |  |
| 7. Control Operations All 9 dozers are demobing today. |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by (Resource Unit Leader) |  |  | Approved by (Planning Section Chief) Franco Nogarin |  |  |  |  | Date prepared July 17th, 2015 |  |  | Time 1800 |

| # ASSIGNMENT LIST – Paradise Branch |  |  |  | Channel Frequency: 5 |  |  |  |  |  | 2. Division/Group Alpha/Bravo |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name Swampy Paradise Complex |  |  |  | 4. Operational Period July 18 0900-2100 |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief | Edwin Gillis |  |  | Ignition |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  | Leader |  |  | Number Persons | Trans. Needed | Notes |  |  |  |  |
| SS 10 |  | Lucas |  |  | 4 |  | Ontario Demobs today. |  |  |  |  |
| ON 98 |  | Westby |  |  | 4 |  |  |  |  |  |  |
| ON 99 |  | Saville |  |  | 4 |  |  |  |  |  |  |
| ON 102 |  | Brignall |  |  | 4 |  |  |  |  |  |  |
| Paradise EFF #1 |  | Scott King |  |  | 5 |  |  |  |  |  |  |
| Paradise EFF #2 |  | Tyler |  |  | 5 |  |  |  |  |  |  |
| Ss 8 |  | Unknown |  |  | 5 |  |  |  |  |  |  |
| 7. Control Operations Focus on hotspots near H18. Crews working the line |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by (Resource Unit Leader) |  |  | Approved by (Planning Section Chief) Franco Nogarin |  |  |  |  | Date July 17th, 2015 |  |  | Time 1800 |

| # ASSIGNMENT LIST – Swampy Branch |  |  |  | Channel Frequency: 10 |  |  |  |  |  | 2. Division/Group |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name Swampy Paradise Complex |  |  |  | 4. Operational Period July 18 0900-2100 |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief | Edwin Gillis |  |  | Ignition |  |  |  |  |  |  |  |
| Branch Director | Lyle Froehlich |  |  | VPS |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  | Leader |  |  | Number Persons | Trans. Needed | Notes |  |  |  |  |
| Swampy EFF #1 (SS028) |  |  |  |  | 5 |  |  |  |  |  |  |
| SS 06 (SS073) |  | Eddie B. |  |  | 5 |  |  |  |  |  |  |
| ON 100 (SS073) |  |  |  |  | 5 |  |  |  |  |  |  |
| 7. Control Operations Crews will be assigned to work areas of concern as per the Branch Directors instructions |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by (Resource Unit Leader) |  |  | Approved by (Planning Section Chief) Franco Nogarin |  |  |  |  | Date July 17th, 2015 |  |  | Time 1800 |

| # SUMMARY OF CURRENT ACTIONS |  |  |
| --- | --- | --- |
| For period: Overview Objectives are still being met. Further Ignition will only be carried out as a contingency if the fire threatens values. Suppression of hotspots while the weather remains cooperative continues. Summary of Actions undertaken and results: Paradise - Cat Guard 100% complete 9 Dozers Demob today - Gravel Pit Cabin demob Today. - No Bucketing again yesterday, Crews have a good handle on this fire crews continue to work the line with a single hotspot left to complete. - Ontario Demob today - Continue to work the problem area near H18, nearly complete - Complete sling pad to facilitate removal of equipment. Swampy - Southern powerline hotspots complete, working remaining hotspot to the east - Yesterday Burn failed – Today Ignition operation on the NE flank – weather permitting - #73 UC. Consultation & Engagement: - IC Team Brief at 0800; Debrief w IC Team at 1900. - Brief at Paradise Garden with crew at 0900. - Distributed daily IAP to THR Fire Chief Potter at 0800. - Continue distributing daily IAP to appropriate personnel. - Distribute daily IAP to Regional Office & Warehouse. Posted daily for their information. - Transfer updated maps to cutouts & distribute/post. - Debrief w NB ICTeam in Fort Providence on “best practices” w IC Daniel & IC Brent. - Liaise with Enterprise. Verbal update & supply IAP/map. - Liaise with KFN. Verbal update & supply IAP/map. - Telephone update with HRMC & WPFN. - Prepare for transition w Raelene, new IO. Problems/Concerns: Hotspots buned quite deep making them difficult to extinguish Observed Wx: At 1300 T21/21.5 RH55/63 Winds WNW11/NW15 for Paradise and Swampy respectively. |  |  |
| Time: 1800 | Date Prepared: July 17th, 2015 | Franco Nogarin |

| # MEDICAL PLAN |  |  | 1. INCIDENT NAME |  |  |  |  | 2 DATE PREPARED |  | 3. TIME PREPARED |  |  | 4. OPERATIONAL PERIOD |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Paradise Complex |  |  |  |  | July 17, 2015 |  | 1600 Hrs |  |  | July 18 0900-2100 |  |  |  |  |  |
| 5. INCIDENT MEDICAL AID STATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MEDICAL AID STATIONS |  |  |  |  |  | LOCATION |  |  |  |  |  |  |  |  |  |  | MEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| Hay River Hospital via Hay River Airport See workflow below… |  |  |  |  |  | Hay River |  |  |  |  |  |  |  |  |  |  | X |  |
| 6. TRANSPORTATION The medivac machine for Paradise is IUX, the medivac machine for Swampy is GKO |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A. AMBULANCE SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  |  |  | ADDRESS |  |  |  |  |  |  |  | PHONE |  |  |  |  | PARAMEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| Hay River Ambulance |  |  |  | Hay River |  |  |  |  |  |  |  | 874-9333 |  |  |  |  | X |  |
| B. INCIDENT AMBULANCES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  |  |  | LOCATION |  |  |  |  |  |  |  |  |  |  |  |  | PARAMEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| **As Indicated Above |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. HOSPITALS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  | ADDRESS |  |  | TRAVEL TIME |  |  |  | PHONE |  |  |  |  | HELIPAD |  | BURN CENTER |  |  |
|  |  |  |  |  | AIR |  | GRND |  |  |  |  |  |  | YES | NO | YES |  | NO |
| Hay River Hospital |  | 3 Gaetz Drive |  |  |  |  | 30m |  | 867-874-7100 |  |  |  |  |  | X |  |  | X |
| Yellowknife Stanton Hosp. |  | Yellowknife |  |  |  |  |  |  | 867-920-7777 |  |  |  |  | X |  |  |  | X |
| Burn Unit |  | Edmonton |  |  |  |  |  |  |  |  |  |  |  | X |  | X |  |  |
| H.R.Hosp. Dir. Client Services – Sheryl Courtoreille (RN) |  |  |  |  |  |  |  |  | 867-874-7162 |  |  |  |  |  |  |  |  |  |
| 8. MEDICAL EMERGENCY PROCEDURES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Call hospital ahead of time and give # of injured, Nature of injuries and names if the injured. Incidents requiring medevac – Transport to the airport near main building. Hay river hospital will send emergency team to the airport to transport injured to HR Hospital – They request a crew member travel to the hospital to aid in answering questions. Give them ENR contact number of 867-874-8225. Info requested by Hospital on injured personnel: - Date of birth - Home Address - Next of Kin - Heath Card Info |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 206 ICS 8/78 | 9. PREPARED BY Franco Nogarin |  |  |  |  |  |  |  |  |  | 10. REVIEWED BY John Ongo |  |  |  |  |  |  |  |

# Incident Org Chart

| # INCIDENT COMMUNICATIONS PLAN |  |  | 1. INCIDENT NAME |  |  | 2. DATE/TIME PREPARED | 3. OPERATIONAL PERIOD DATE/TIME |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Paradise Complex |  |  | July 17th, 2000 | July 18th, 0900-2100 |  |
| Paradise Branch |  |  |  |  |  |  |  |  |
| Assigned to | FUNCTION | CHANNEL |  | Simplex/Duplex | REMARKS |  |  |
| All Crews | Ground Ops | 5 |  | 153.47 |  |  |  |
| Ignition | Ignition Operations | 14 |  | 161.535 | All aircraft should monitor 122.05 am |  |  |
| Swampy Branch |  |  |  |  |  |  |  |
| Swampy Branch | Ground Operations | 10 |  |  |  |  |  |
| Swampy Branch | Air Operations | 9 |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |
| 5. PREPARED BY Franco Nogarin |  |  |  |  |  |  |  |  |

# HELICOPTERS

Paradise

CALL SIGN		TYPE			MAKE		PILOT			Contract Ends

IUX			Intermediate		A-STAR	Jordan Hatch

SLY			Intermediate		350B-2	Felix Christians	July 18, 2015

Swampy

GKO			Intermediate		350B-2	Vern Brodhagen 	July 18, 2015

All Helicopters will continue to check in with XLI 55 for 30 minute check in

The medevac machine for Paradise is IUX

The medevac machine for Swampy is GKO

# MOB

| DATE | POSITION/TYPE | NAME | DESTINATION | TRANSPORT | Notes |
| --- | --- | --- | --- | --- | --- |

# NEW RESOURCE REQUEST

| RESOURCE NEED | DATE REQUIRED | DESTINATION | NOTES |
| --- | --- | --- | --- |

# OUTSTANDING ORDERS

| RESOURCE NEED | DATE REQUIRED | DATE REQUESTED | DESTINATION | NOTES |
| --- | --- | --- | --- | --- |

# DEMOB

| DATE | POSITION/TYPE | NAME | DESTINATION | TRANSPORT | Notes |
| --- | --- | --- | --- | --- | --- |
| July 18 | ON98, ON 99, ON 100 & ON102 | With Arep Nick Edey | Ont | Charter | 42 Souls |
| July 23 | FBAN | Dustin Oikle | NS | Sched |  |
| July 23 | Ops | Edwin Gillis | PEI | Sched |  |
| July 23 | Safety | John Ongo | NS | Sched |  |
| July 24 | Fin/Adm | Emily M. | YFS |  |  |

SWAMPY PARADISE COMPLEX (SS-037) CONTACT INFORMATION

INCIDENT MANAGEMENT TEAM

Position	Name	Phone Number

IC	Brent Starling	(867) 872-0486

Plans	Franco Nogarin	(867) 872-0393

FBAN	Dustin Oikle	(902) 956-4125

Div Sup	Manny Vital	(250) 321-0767

Ops	Edwin Gillis	(902) 432-2484

Swampy Branch Director	Lyle Froehlich	(867) 875-2504

Logistics	Daniel Lund	(867) 695-6676

Fin/Admin & Resource Unit	Emily McInnis-Wharton	(867) 444-8586

Fin/Admin & Time Unit	Raelene Lamalice	(867) 874-8225

Safety Officer	John Ongo	(902) 577-0930

Safety Officer	Jordyn Siurko	(867) 876-0601

Regional Office Duty Officer	Gerry Hordal	(867) 875-7443

District Area Office		(867) 875-5558

District Area Office Fire Clerk		(867) 875-5555

Incident Command Post	Raelene Lamalice	(867) 874-8225

Ontario A/Rep	Nick Edey	(807) 863-0026

Community Contacts

Mayor Andrew Cassidy	(867) 876-0528

Hay River Fire Chief, Ross Potter	(867) 876-0279

Hay River Ambulance Service	(867) 874-9333

Katl’odeeche First Nation Chief Roy Fabian	(867) 876-0079

Enterprise Mayor John Leskiw	(867) 984-3666

West Point First Nation	(867) 874-6677

Hay River Metis Council	(867) 874-4470

Dept. of Highways – Darin Murphy…………	(867) 875-7344

Dept. of Highways – Roy Norwegian	(867) 984-3421