Incident Action Plan

JULY 19th, 2015

SWAMPY

PARADISE COMPLEX

Wildfires SS027-15, SS028-15, SS036-15, SS073-15 (Swampy Lakes)

Wildfires SS037, SS065 (Paradise Gardens)

| # INCIDENT OBJECTIVES |  | . INCIDENT NAME |  |  | . DATE PREPARED | . TIME PREPARED |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Swampy Paradise Complex |  |  | July 18th, 2015 | 1800 |
| OPERATIONAL PERIOD (DATE/TIME) |  |  |  |  |  |  |
| July 19th, 2015 0900 - 2100 |  |  |  |  |  |  |
| GENERAL NOTE: This team is protecting the community of Hay River, the K’atlodeeche reserve and the sub-divisions of the Hay River corridor as well as managing the Swampy fire to ensure values in the area are not threatened. |  |  |  |  |  |  |
| GENERAL CONTROL OBJECTIVES FOR THE INCIDENT (INCLUDE ALTERNATIVES) OPS: Paradise Continue work to complete the problem area near H18 Crews continue working the line with one hot spot left to complete. Crews will continue to monitor the perimeter for hotspots Swampy working remaining hotspot to the east Ignition operation on the NW flank – if weather permitting and we have the helicopters. Likely ready to hand back to region by Tuesday #73 UC. Being mopped up. |  |  |  |  |  |  |
| Weather: |  |  |  |  |  |  |
| Max Temp Min RH Wind Rain Paradise; 19; 60%; N25G35; Rain 10-15 mm. Swampy; 19; 40%; N25G35; Chance of 1-2 mm. |
| GENERAL SAFETY MESSAGE |  |  |  |  |  |  |
| 1.Hazards and Risks: - Hazard trees – Heads up for hazardous trees or snags – warn others around you and insure that any hazard trees are flagged. - Fatigue/personal welfare – Take care of yourself by getting adequate rest and eating properly. The end of your shift is days away so do not let yourself get worn out. - Complacency – Stay vigilant and expect the unexpected. Familiarity can lead to complacency - Be aware of possible new fire starts from lightning in your working area 2. Communications: - All Firefighters are responsible for communication hazards to others and to brief others as needed - Ensure radio frequencies are confirmed - Always provide an update on any situation change - Keep informed on weather conditions and forecasts 3. Fire Order of the Day: Know what your fire is doing at all times 4. Watch Out Situation: Unfamiliar with weather and local factors influencing fire behavior. 5. Maintain Situational Awareness - Initiate all actions based on safety as a first priority - Swampy: poor comms at swampy – Lyle to check-in at HR-ENR 3 times/day at 876-874-8225 |  |  |  |  |  |  |
| PREPARED BY (PLANNING SECTION CHIEF) |  |  | APPROVED BY (INCIDENT COMMANDER) |  |  |  |
| Franco Nogarin |  |  | Brent Starling |  |  |  |

# Fire Behaviour Forecast for Paradise

# Fire Behaviour Forecast for Swampy

| # ASSIGNMENT LIST – Paradise Branch |  |  |  | Channel Frequency: 5 |  |  |  |  |  | 2. Division/Group Alpha/Bravo |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name Swampy Paradise Complex |  |  |  | 4. Operational Period July 19 0900-2100 |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief | Edwin Gillis |  |  | Ignition |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  | Leader |  |  | Number Persons | Trans. Needed | Notes |  |  |  |  |
| SS 10 |  | Lucas |  |  | 4 |  |  |  |  |  |  |
| Paradise EFF #1 |  | Scott King |  |  | 5 |  |  |  |  |  |  |
| Paradise EFF #2 |  | Tyler |  |  | 5 |  |  |  |  |  |  |
| Paradise EFF #3 |  | Conrad |  |  | 5 |  |  |  |  |  |  |
| Ss 8 |  | Eric |  |  | 5 |  |  |  |  |  |  |
| 7. Control Operations Focus on hotspots near H18. Monitor the perimeter for hotspots Crews working the problem area |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by (Resource Unit Leader) Emily McInnis-Wharton |  |  | Approved by (Planning Section Chief) Franco Nogarin |  |  |  |  | Date July 18th, 2015 |  |  | Time 1800 |

| # ASSIGNMENT LIST – Swampy Branch |  |  |  | Channel Frequency: 10 |  |  |  |  |  | 2. Division/Group |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name Swampy Paradise Complex |  |  |  | 4. Operational Period July 19 0900-2100 |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief | Edwin Gillis |  |  | Ignition |  |  |  |  |  |  |  |
| Branch Director | Lyle Froehlich |  |  | VPS |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  | Leader |  |  | Number Persons | Trans. Needed | Notes |  |  |  |  |
| Swampy EFF #1 (SS028) |  | Sam |  |  | 5 |  |  |  |  |  |  |
| SS 06 (SS073) |  | Pierre |  |  | 4 |  |  |  |  |  |  |
| 7. Control Operations Crews will be assigned to work areas of concern as per the Branch Directors instructions Mopup on #73 |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by (Resource Unit Leader) Emily McInnis-Wharton |  |  | Approved by (Planning Section Chief) Franco Nogarin |  |  |  |  | Date July 18th, 2015 |  |  | Time 1800 |

| # SUMMARY OF CURRENT ACTIONS |  |  |
| --- | --- | --- |
| For period: Overview Objectives are still being met. Further Ignition will only be carried out as a contingency if the fire threatens values. Suppression of hotspots while the weather remains cooperative continues. Summary of Actions undertaken and results: Paradise - 9 Dozers Demobed - Gravel Pit Cabin demobed - Crews worked the Problem area until it flared up flared up – 2 machines bucketed until it settled. - Ontario Demobed - Sling pad to facilitate removal of equipment completed and much equipment removed. Swampy - working remaining hotspot to the east - Yesterday Burn failed again – Today Ignition operation on the NW flank – weather permitting - #73 UC. – Mopping up Consultation & Engagement: - IC Team Brief at 0800; Debrief w IC Team at 1900. - Brief at Paradise Garden with crew at 0900. - Distributed daily IAP to THR Fire Chief Potter at 0800. - Continue distributing daily IAP to appropriate personnel. - Distribute daily IAP to Regional Office & Warehouse. Posted daily for their information. - Transfer updated maps to cutouts & distribute/post. - No planned local government consultation until tribal groups return from Lac Ste. Anne. Continue Update with THR. Problems/Concerns: Hotspots buned quite deep making them difficult to extinguish Observed Wx: At 1300 T:25.5/23.5 RH:39/62 Winds:NW11G23/N-Light Rain:0/0 for Paradise and Swampy respectively. |  |  |
| Time: 1800 | Date Prepared: July 18th, 2015 | Franco Nogarin |

| # MEDICAL PLAN |  |  | 1. INCIDENT NAME |  |  |  |  | 2 DATE PREPARED |  | 3. TIME PREPARED |  |  | 4. OPERATIONAL PERIOD |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Paradise Complex |  |  |  |  | July 18, 2015 |  | 1600 Hrs |  |  | July 19 0900-2100 |  |  |  |  |  |
| 5. INCIDENT MEDICAL AID STATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MEDICAL AID STATIONS |  |  |  |  |  | LOCATION |  |  |  |  |  |  |  |  |  |  | MEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| Hay River Hospital via Hay River Airport See workflow below… |  |  |  |  |  | Hay River |  |  |  |  |  |  |  |  |  |  | X |  |
| 6. TRANSPORTATION The medivac machine for Paradise is BUC, the medivac machine for Swampy is JKN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A. AMBULANCE SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  |  |  | ADDRESS |  |  |  |  |  |  |  | PHONE |  |  |  |  | PARAMEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| Hay River Ambulance |  |  |  | Hay River |  |  |  |  |  |  |  | 874-9333 |  |  |  |  | X |  |
| B. INCIDENT AMBULANCES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  |  |  | LOCATION |  |  |  |  |  |  |  |  |  |  |  |  | PARAMEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| **As Indicated Above |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. HOSPITALS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  | ADDRESS |  |  | TRAVEL TIME |  |  |  | PHONE |  |  |  |  | HELIPAD |  | BURN CENTER |  |  |
|  |  |  |  |  | AIR |  | GRND |  |  |  |  |  |  | YES | NO | YES |  | NO |
| Hay River Hospital |  | 3 Gaetz Drive |  |  |  |  | 30m |  | 867-874-7100 |  |  |  |  |  | X |  |  | X |
| Yellowknife Stanton Hosp. |  | Yellowknife |  |  |  |  |  |  | 867-920-7777 |  |  |  |  | X |  |  |  | X |
| Burn Unit |  | Edmonton |  |  |  |  |  |  |  |  |  |  |  | X |  | X |  |  |
| H.R.Hosp. Dir. Client Services – Sheryl Courtoreille (RN) |  |  |  |  |  |  |  |  | 867-874-7162 |  |  |  |  |  |  |  |  |  |
| 8. MEDICAL EMERGENCY PROCEDURES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Call hospital ahead of time and give # of injured, Nature of injuries and names if the injured. Incidents requiring medevac – Transport to the airport near main building. Hay river hospital will send emergency team to the airport to transport injured to HR Hospital – They request a crew member travel to the hospital to aid in answering questions. Give them ENR contact number of 867-874-8225. Info requested by Hospital on injured personnel: - Date of birth - Home Address - Next of Kin - Heath Card Info |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 206 ICS 8/78 | 9. PREPARED BY Franco Nogarin |  |  |  |  |  |  |  |  |  | 10. REVIEWED BY John Ongo |  |  |  |  |  |  |  |

# Incident Org Chart

| # INCIDENT COMMUNICATIONS PLAN |  |  | 1. INCIDENT NAME |  |  | 2. DATE/TIME PREPARED | 3. OPERATIONAL PERIOD DATE/TIME |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Paradise Complex |  |  | July 18th, 2000 | July 19th, 0900-2100 |  |
| Paradise Branch |  |  |  |  |  |  |  |  |
| Assigned to | FUNCTION | CHANNEL |  | Simplex/Duplex | REMARKS |  |  |
| All Crews | Ground Ops | 5 |  | 153.47 |  |  |  |
| Ignition | Ignition Operations | 14 |  | 161.535 | All aircraft should monitor 122.05 am |  |  |
| Swampy Branch |  |  |  |  |  |  |  |
| Swampy Branch | Ground Operations | 10 |  |  |  |  |  |
| Swampy Branch | Air Operations | 9 |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |
| 5. PREPARED BY Franco Nogarin |  |  |  |  |  |  |  |  |

# HELICOPTERS

Paradise

CALL SIGN		TYPE			MAKE		PILOT			Contract Ends

BUC			Medium		212		?

Swampy

JKN			Medium		205

All Helicopters will continue to check in with XLI 55 for 30 minute check in

The medevac machine for Paradise is BUC

The medevac machine for Swampy is JKN

# MOB

| DATE | POSITION/TYPE | NAME | DESTINATION | TRANSPORT | Notes |
| --- | --- | --- | --- | --- | --- |

# NEW RESOURCE REQUEST

| RESOURCE NEED | DATE REQUIRED | DESTINATION | NOTES |
| --- | --- | --- | --- |

# OUTSTANDING ORDERS

| RESOURCE NEED | DATE REQUIRED | DATE REQUESTED | DESTINATION | NOTES |
| --- | --- | --- | --- | --- |

# DEMOB

| DATE | POSITION/TYPE | NAME | DESTINATION | TRANSPORT | Notes |
| --- | --- | --- | --- | --- | --- |
| July 23 | FBAN | Dustin Oikle | NS | Sched |  |
| July 23 | Ops | Edwin Gillis | PEI | Sched |  |
| July 23 | Safety | John Ongo | NS | Sched |  |
| July 24 | Fin/Adm | Emily M. | YFS |  |  |

SWAMPY PARADISE COMPLEX (SS-037) CONTACT INFORMATION

INCIDENT MANAGEMENT TEAM

Position	Name	Phone Number

IC	Brent Starling	(867) 872-0486

Plans	Franco Nogarin	(867) 872-0393

FBAN	Dustin Oikle	(902) 956-4125

Div Sup	Manny Vital	(250) 321-0767

Ops	Edwin Gillis	(902) 432-2484

Swampy Branch Director	Lyle Froehlich	(867) 875-2504

Logistics	Daniel Lund	(867) 695-6676

Fin/Admin & Resource Unit	Emily McInnis-Wharton	(867) 444-8586

Fin/Admin & Time Unit	Raelene Lamalice	(867) 874-8225

Safety Officer	John Ongo	(902) 577-0930

Safety Officer	Jordyn Siurko	(867) 876-0601

Regional Office Duty Officer	Gerry Hordal	(867) 875-7443

District Area Office		(867) 875-5558

District Area Office Fire Clerk		(867) 875-5555

Incident Command Post	Raelene Lamalice	(867) 874-8225

Community Contacts

Mayor Andrew Cassidy	(867) 876-0528

Hay River Fire Chief, Ross Potter	(867) 876-0279

Hay River Ambulance Service	(867) 874-9333

Katl’odeeche First Nation Chief Roy Fabian	(867) 876-0079

Enterprise Mayor John Leskiw	(867) 984-3666

West Point First Nation	(867) 874-6677

Hay River Metis Council	(867) 874-4470

Dept. of Highways – Darin Murphy…………	(867) 875-7344

Dept. of Highways – Roy Norwegian	(867) 984-3421