Incident Action Plan

JULY 20th, 2015

SWAMPY

PARADISE COMPLEX

Wildfires SS027-15, SS028-15, SS036-15, SS073-15 (Swampy Lakes)

Wildfires SS037, SS065 (Paradise Gardens)

| # INCIDENT OBJECTIVES |  | . INCIDENT NAME |  |  | . DATE PREPARED | . TIME PREPARED |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Swampy Paradise Complex |  |  | July 19th, 2015 | 1800 |
| OPERATIONAL PERIOD (DATE/TIME) |  |  |  |  |  |  |
| July 20th, 2015 0900 - 2100 |  |  |  |  |  |  |
| GENERAL NOTE: This team is protecting the community of Hay River, the K’atlodeeche reserve and the sub-divisions of the Hay River corridor as well as managing the Swampy fire to ensure values in the area are not threatened. |  |  |  |  |  |  |
| GENERAL CONTROL OBJECTIVES FOR THE INCIDENT (INCLUDE ALTERNATIVES) OPS: Paradise - Continue work to complete the problem area near H18 - Finish the blackline on the problem area. - Crews will continue to monitor the perimeter for hotspots - Sling out 5-6 drums of Cat fuel, and 15-20 Empties - Scan the problem area in the AM Swampy #28 – Monitor the fire and initiate demob #73 UC. |  |  |  |  |  |  |
| Weather: Paradise Max Temp: 21.5, Low RH: 40%, Winds: Variable 10kph becoming easterly 10G20kph late day, Rain: Chance of showers.. |
| Swampy Max Temp: 20, Low RH: 40%, Winds: Variable 10kph becoming easterly 10G20kph late day, Rain: Chance of showers.. |
| GENERAL SAFETY MESSAGE |  |  |  |  |  |  |
| - Remember LACES - LACES - LACES - Hazard trees and snags - Maintain Situation Awareness - Swampy: poor comms at swampy – Lyle to check-in at HR-ENR 3 times/day at 876-874-8225 - Watch-out Situation of the Day: Terrain & Fuels make Escape to Safety Zones Difficult - Paradise Medivac is JKN - Swampy Medivac is ZFN |  |  |  |  |  |  |
| PREPARED BY (PLANNING SECTION CHIEF) |  |  | APPROVED BY (INCIDENT COMMANDER) |  |  |  |
| Franco Nogarin |  |  | Brent Starling |  |  |  |

# Fire Behaviour Forecast for Paradise

# Fire Behaviour Forecast for Swampy

| # ASSIGNMENT LIST – Paradise Branch |  |  |  | Channel Frequency: 5 |  |  |  |  |  | 2. Division/Group Alpha/Bravo |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name Swampy Paradise Complex |  |  |  | 4. Operational Period July 20 0900-2100 |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief | Edwin Gillis |  |  | Ignition |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  | Leader |  |  | Number Persons | Trans. Needed | Notes |  |  |  |  |
| SS 10 |  | Lucas |  |  | 4 |  |  |  |  |  |  |
| Paradise EFF #1 |  | Scott King |  |  | 3 |  |  |  |  |  |  |
| Paradise EFF #2 |  | Tyler |  |  | 5 |  |  |  |  |  |  |
| Paradise EFF #3 |  | Conrad |  |  | 5 |  |  |  |  |  |  |
| Ss 8 |  | Eric |  |  | 5 |  |  |  |  |  |  |
| 7. Control Operations Complete the blackline on problem area near H18. Monitor the perimeter for hotspots Sling out Cat fuel and empties |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by (Resource Unit Leader) Emily McInnis-Wharton |  |  | Approved by (Planning Section Chief) Franco Nogarin |  |  |  |  | Date July 19th, 2015 |  |  | Time 1800 |

| # ASSIGNMENT LIST – Swampy Branch |  |  |  | Channel Frequency: 10 |  |  |  |  |  | 2. Division/Group |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name Swampy Paradise Complex |  |  |  | 4. Operational Period July 20 0900-2100 |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief | Edwin Gillis |  |  | Ignition |  |  |  |  |  |  |  |
| Branch Director | Lyle Froehlich |  |  | VPS |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  | Leader |  |  | Number Persons | Trans. Needed | Notes |  |  |  |  |
| Swampy EFF #1 (SS028) |  | Sam |  |  | 5 |  |  |  |  |  |  |
| SS 06 (SS073) |  | Pierre |  |  | 4 |  |  |  |  |  |  |
| 7. Control Operations Crews will be assigned to work areas of concern as per the Branch Directors instructions #73 UC complete the Cold trail #28 Initiate demob by end of day. |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by (Resource Unit Leader) Emily McInnis-Wharton |  |  | Approved by (Planning Section Chief) Franco Nogarin |  |  |  |  | Date July 19th, 2015 |  |  | Time 1800 |

| # SUMMARY OF CURRENT ACTIONS |  |  |
| --- | --- | --- |
| For period: Overview Objectives are still being met. Further Ignition will only be carried out as a contingency if the fire threatens values. Suppression of hotspots while the weather remains cooperative continues. Summary of Actions undertaken and results: Paradise - Crews worked the Problem area and completed the blackline on the remaining spot, and got a good chunk of the blacking on the problem area done. - Continue to monitor the fire. Swampy - #28 Monitord the fire - #73 UC. – Mopped up and beefed up the blackline Consultation & Engagement: - IC Team Brief at 0800; Debrief w IC Team at 1900. - Brief at Paradise Garden with crew at 0900. - Distributed daily IAP to THR Fire Chief Potter at 0800. - Continue distributing daily IAP to appropriate personnel. - Distribute daily IAP to Regional Office & Warehouse. Posted daily for their information. - Transfer updated maps to cutouts & distribute/post. - No planned local government consultation until tribal groups return from Lac Ste. Anne. Continue Update with THR. Problems/Concerns: Hotspots buned quite deep making them difficult to extinguish Observed Wx: At 1300 T:17.5/18 RH:72/68 Winds:NW8.5G16/N10G20 Rain:10/0 for Paradise and Swampy respectively. |  |  |
| Time: 1800 | Date Prepared: July 19th, 2015 | Franco Nogarin |

| # MEDICAL PLAN |  |  | 1. INCIDENT NAME |  |  |  |  | 2 DATE PREPARED |  | 3. TIME PREPARED |  |  | 4. OPERATIONAL PERIOD |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Paradise Complex |  |  |  |  | July 19, 2015 |  | 1600 Hrs |  |  | July 20 0900-2100 |  |  |  |  |  |
| 5. INCIDENT MEDICAL AID STATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MEDICAL AID STATIONS |  |  |  |  |  | LOCATION |  |  |  |  |  |  |  |  |  |  | MEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| Hay River Hospital via Hay River Airport See workflow below… |  |  |  |  |  | Hay River |  |  |  |  |  |  |  |  |  |  | X |  |
| 6. TRANSPORTATION The medivac machine for Paradise is JKN, the medivac machine for Swampy is ZFN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A. AMBULANCE SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  |  |  | ADDRESS |  |  |  |  |  |  |  | PHONE |  |  |  |  | PARAMEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| Hay River Ambulance |  |  |  | Hay River |  |  |  |  |  |  |  | 874-9333 |  |  |  |  | X |  |
| B. INCIDENT AMBULANCES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  |  |  | LOCATION |  |  |  |  |  |  |  |  |  |  |  |  | PARAMEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| **As Indicated Above |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. HOSPITALS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  | ADDRESS |  |  | TRAVEL TIME |  |  |  | PHONE |  |  |  |  | HELIPAD |  | BURN CENTER |  |  |
|  |  |  |  |  | AIR |  | GRND |  |  |  |  |  |  | YES | NO | YES |  | NO |
| Hay River Hospital |  | 3 Gaetz Drive |  |  |  |  | 30m |  | 867-874-7100 |  |  |  |  |  | X |  |  | X |
| Yellowknife Stanton Hosp. |  | Yellowknife |  |  |  |  |  |  | 867-920-7777 |  |  |  |  | X |  |  |  | X |
| Burn Unit |  | Edmonton |  |  |  |  |  |  |  |  |  |  |  | X |  | X |  |  |
| H.R.Hosp. Dir. Client Services – Sheryl Courtoreille (RN) |  |  |  |  |  |  |  |  | 867-874-7162 |  |  |  |  |  |  |  |  |  |
| 8. MEDICAL EMERGENCY PROCEDURES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Call hospital ahead of time and give # of injured, Nature of injuries and names if the injured. Incidents requiring medevac – Transport to the airport near main building. Hay river hospital will send emergency team to the airport to transport injured to HR Hospital – They request a crew member travel to the hospital to aid in answering questions. Give them ENR contact number of 867-874-8225. Info requested by Hospital on injured personnel: - Date of birth - Home Address - Next of Kin - Heath Card Info |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 206 ICS 8/78 | 9. PREPARED BY Franco Nogarin |  |  |  |  |  |  |  |  |  | 10. REVIEWED BY John Ongo |  |  |  |  |  |  |  |

# Incident Org Chart

| # INCIDENT COMMUNICATIONS PLAN |  |  | 1. INCIDENT NAME |  |  | 2. DATE/TIME PREPARED | 3. OPERATIONAL PERIOD DATE/TIME |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Paradise Complex |  |  | July 19th, 2000 | July 20th, 0900-2100 |  |
| Paradise Branch |  |  |  |  |  |  |  |  |
| Assigned to | FUNCTION | CHANNEL |  | Simplex/Duplex | REMARKS |  |  |
| All Crews | Ground Ops | 5 |  | 153.47 |  |  |  |
| Ignition | Ignition Operations | 14 |  | 161.535 | All aircraft should monitor 122.05 am |  |  |
| Swampy Branch |  |  |  |  |  |  |  |
| Swampy Branch | Ground Operations | 10 |  |  |  |  |  |
| Swampy Branch | Air Operations | 9 |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |
| 5. PREPARED BY Franco Nogarin |  |  |  |  |  |  |  |  |

# HELICOPTERS

Paradise

CALL SIGN		TYPE			MAKE		PILOT		Medivac for

JKN			Medium		205		?	 	Paradise

Swampy

ZFN			Intermediate		AS350B2	?		Swampy

All Helicopters will continue to check in with XLI 55 for 30 minute check in

# MOB

| DATE | POSITION/TYPE | NAME | DESTINATION | TRANSPORT | Notes |
| --- | --- | --- | --- | --- | --- |

# NEW RESOURCE REQUEST

| RESOURCE NEED | DATE REQUIRED | DESTINATION | NOTES |
| --- | --- | --- | --- |

# OUTSTANDING ORDERS

| RESOURCE NEED | DATE REQUIRED | DATE REQUESTED | DESTINATION | NOTES |
| --- | --- | --- | --- | --- |

# DEMOB

| DATE | POSITION/TYPE | NAME | DESTINATION | TRANSPORT | Notes |
| --- | --- | --- | --- | --- | --- |
| July 23 | IC | Brent Starling | YSM | sched | Flights need booking |
| July 23 | Plans | F. Nogarin | YSM | sched | Flights need booking |
| July 23 | Logs | Daniel Lund | YFS | Pers. Veh. |  |
| July 23 | Ass. Safety | Jordyn Siurko | Fort Res | ENR Truck |  |
| July 23 | FBAN | Dustin Oikle | HALIFAX | Sched | Flights need booking |
| July 23 | Ops | Edwin Gillis | HALIFAX | Sched | Flights need booking |
| July 23 | Safety | John Ongo | HALIFAX | Sched | Flights need booking |
| July 23 | Fin/Adm | Emily McInnis-Wharton | YFS | Pers. Veh. |  |
| July 23 | Div Sup | Manny Vital | YJF | ENR Truck |  |

SWAMPY PARADISE COMPLEX (SS-037) CONTACT INFORMATION

INCIDENT MANAGEMENT TEAM

Position	Name	Phone Number

IC	Brent Starling	(867) 872-0486

Plans	Franco Nogarin	(867) 872-0393

FBAN	Dustin Oikle	(902) 956-4125

Div Sup	Manny Vital	(250) 321-0767

Ops	Edwin Gillis	(902) 432-2484

Swampy Branch Director	Lyle Froehlich	(867) 875-2504

Logistics	Daniel Lund	(867) 695-6676

Fin/Admin & Resource Unit	Emily McInnis-Wharton	(867) 444-8586

Fin/Admin & Time Unit	Raelene Lamalice	(867) 874-8225

Safety Officer	John Ongo	(902) 577-0930

Safety Officer	Jordyn Siurko	(867) 876-0601

Regional Office Duty Officer	Gerry Hordal	(867) 875-7443

District Area Office		(867) 875-5558

District Area Office Fire Clerk		(867) 875-5555

Incident Command Post	Raelene Lamalice	(867) 874-8225

Community Contacts

Mayor Andrew Cassidy	(867) 876-0528

Hay River Fire Chief, Ross Potter	(867) 876-0279

Hay River Ambulance Service	(867) 874-9333

Katl’odeeche First Nation Chief Roy Fabian	(867) 876-0079

Enterprise Mayor John Leskiw	(867) 984-3666

West Point First Nation	(867) 874-6677

Hay River Metis Council	(867) 874-4470

Dept. of Highways – Darin Murphy…………	(867) 875-7344

Dept. of Highways – Roy Norwegian	(867) 984-3421