Incident Action Plan

JULY 21th, 2015

SWAMPY

PARADISE COMPLEX

Wildfires SS027-15, SS028-15, SS036-15, SS073-15 (Swampy Lakes)

Wildfires SS037, SS065 (Paradise Gardens)

| # INCIDENT OBJECTIVES |  | . INCIDENT NAME |  |  | . DATE PREPARED | . TIME PREPARED |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Swampy Paradise Complex |  |  | July 20th, 2015 | 1800 |
| OPERATIONAL PERIOD (DATE/TIME) |  |  |  |  |  |  |
| July 21th, 2015 0900 - 2100 |  |  |  |  |  |  |
| GENERAL NOTE: This team is protecting the community of Hay River, the K’atlodeeche reserve and the sub-divisions of the Hay River corridor as well as managing the Swampy fire to ensure values in the area are not threatened. |  |  |  |  |  |  |
| GENERAL CONTROL OBJECTIVES FOR THE INCIDENT (INCLUDE ALTERNATIVES) OPS: Paradise - Complete the blackline on the problem area by lunch. - Initiate demob of SS037 Swampy - #28 – Monitor the fire - Recon the old airport road and plan for ignition of unburned fuels when conditions permit. - Report back the 1300 weather - #73 UC And Demobed. |  |  |  |  |  |  |
| Weather: Paradise Max Temp: 21, Low RH: 45%, Winds: Northerly 15G25kph.. |
| Swampy Max Temp: 20, Low RH: 45%, Winds: Northerly 15G25kph.. |
| GENERAL SAFETY MESSAGE |  |  |  |  |  |  |
| - Heli Long Lining Equipment from fire SS037. Crews must wear hard hat with ear protectors. Wear safety glasses to protect against sand and dust blowin in your faces. - Demob should be done in an efficient and timely manner but not rushed, Safety must come first. - Paradise Medivac is ZFN |  |  |  |  |  |  |
| PREPARED BY (PLANNING SECTION CHIEF) |  |  | APPROVED BY (INCIDENT COMMANDER) |  |  |  |
| Franco Nogarin |  |  | Brent Starling |  |  |  |

# Fire Behaviour Forecast for Paradise

# Fire Behaviour Forecast for Swampy

| # ASSIGNMENT LIST – Paradise Branch |  |  |  | Channel Frequency: 5 |  |  |  |  |  | 2. Division/Group Alpha/Bravo |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name Swampy Paradise Complex |  |  |  | 4. Operational Period July 21 0900-2100 |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief | Edwin Gillis |  |  | Ignition |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  | Leader |  |  | Number Persons | Trans. Needed | Notes |  |  |  |  |
| SS 10 |  | Lucas |  |  | 4 |  |  |  |  |  |  |
| Paradise EFF #1 |  | Scott King |  |  | 3 |  |  |  |  |  |  |
| Paradise EFF #2 |  | Tyler |  |  | 5 |  |  |  |  |  |  |
| Paradise EFF #3 |  | Conrad |  |  | 5 |  |  |  |  |  |  |
| Ss 8 |  | Eric |  |  | 5 |  |  |  |  |  |  |
| 7. Control Operations Complete the blackline on problem area near H18. Monitor the perimeter for hotspots Demob #37 |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by (Resource Unit Leader) Emily McInnis-Wharton |  |  | Approved by (Planning Section Chief) Franco Nogarin |  |  |  |  | Date July 20th, 2015 |  |  | Time 1800 |

| # ASSIGNMENT LIST – Swampy Branch |  |  |  | Channel Frequency: 10 |  |  |  |  |  | 2. Division/Group |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3. Incident Name Swampy Paradise Complex |  |  |  | 4. Operational Period July 21 0900-2100 |  |  |  |  |  |  |  |
| 5. Operations Personnel |  |  |  |  |  |  |  |  |  |  |  |
| Operations Chief | Edwin Gillis |  |  | Ignition |  |  |  |  |  |  |  |
| Branch Director | Lyle Froehlich |  |  | VPS |  |  |  |  |  |  |  |
| 6. Resources Assigned this Period |  |  |  |  |  |  |  |  |  |  |  |
| Strike Team/Task Force/ Resource Designator |  | Leader |  |  | Number Persons | Trans. Needed | Notes |  |  |  |  |
| 7. Control Operations #28 – Monitor the fire Recon the old airport road and plan for ignition of unburned fuels when conditions permit. Report back the 1300 weather #73 UC And Demobed |  |  |  |  |  |  |  |  |  |  |  |
| 8. Special Instructions |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by (Resource Unit Leader) Emily McInnis-Wharton |  |  | Approved by (Planning Section Chief) Franco Nogarin |  |  |  |  | Date July 20th, 2015 |  |  | Time 1800 |

| # SUMMARY OF CURRENT ACTIONS |  |  |
| --- | --- | --- |
| For period: Overview Objectives are still being met. Further Ignition will only be carried out as a contingency if the fire threatens values. Suppression of hotspots while the weather remains cooperative continues. Summary of Actions undertaken and results: Paradise - Crews worked the Problem area and completed the blackline on the remaining spot, and got 95% of the blacking on the problem area done. - Continue to monitor the fire. - Complete the blackline by noon. Swampy - #28 Monitored the fire - #73 UC. –demobed Consultation & Engagement: - IC Team Brief at 0800; Debrief w IC Team at 1900. - Brief at Paradise Garden with crew at 0900. - Distributed daily IAP to THR Fire Chief Potter at 0800. - Continue distributing daily IAP to appropriate personnel. - Distribute daily IAP to Regional Office & Warehouse. Posted daily for their information. - Transfer updated maps to cutouts & distribute/post. - No planned local government consultation until tribal groups return from Lac Ste. Anne. Continue Update with THR. Problems/Concerns: Hotspots burned quite deep making them difficult to extinguish Observed Wx: At 1300 Paradise: T19, RH58, WS 5, WD NE, RN 0.8 Swampy East: T21, RH59, WS 5G10, WD NW, RN 0 Swampy West: T21, RH59, WS 5G10, WD NW, RN 2.0 |  |  |
| Time: 1800 | Date Prepared: July 20th, 2015 | Franco Nogarin |

| # MEDICAL PLAN |  |  | 1. INCIDENT NAME |  |  |  |  | 2 DATE PREPARED |  | 3. TIME PREPARED |  |  | 4. OPERATIONAL PERIOD |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Paradise Complex |  |  |  |  | July 20, 2015 |  | 1600 Hrs |  |  | July 21 0900-2100 |  |  |  |  |  |
| 5. INCIDENT MEDICAL AID STATIONS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| MEDICAL AID STATIONS |  |  |  |  |  | LOCATION |  |  |  |  |  |  |  |  |  |  | MEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| Hay River Hospital via Hay River Airport See workflow below… |  |  |  |  |  | Hay River |  |  |  |  |  |  |  |  |  |  | X |  |
| 6. TRANSPORTATION The medivac machine for Paradise is ZFN, the medivac machine for Swampy is JKN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A. AMBULANCE SERVICES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  |  |  | ADDRESS |  |  |  |  |  |  |  | PHONE |  |  |  |  | PARAMEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| Hay River Ambulance |  |  |  | Hay River |  |  |  |  |  |  |  | 874-9333 |  |  |  |  | X |  |
| B. INCIDENT AMBULANCES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  |  |  | LOCATION |  |  |  |  |  |  |  |  |  |  |  |  | PARAMEDICS |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | YES | NO |
| **As Indicated Above |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. HOSPITALS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| NAME |  | ADDRESS |  |  | TRAVEL TIME |  |  |  | PHONE |  |  |  |  | HELIPAD |  | BURN CENTER |  |  |
|  |  |  |  |  | AIR |  | GRND |  |  |  |  |  |  | YES | NO | YES |  | NO |
| Hay River Hospital |  | 3 Gaetz Drive |  |  |  |  | 30m |  | 867-874-7100 |  |  |  |  |  | X |  |  | X |
| Yellowknife Stanton Hosp. |  | Yellowknife |  |  |  |  |  |  | 867-920-7777 |  |  |  |  | X |  |  |  | X |
| Burn Unit |  | Edmonton |  |  |  |  |  |  |  |  |  |  |  | X |  | X |  |  |
| H.R.Hosp. Dir. Client Services – Sheryl Courtoreille (RN) |  |  |  |  |  |  |  |  | 867-874-7162 |  |  |  |  |  |  |  |  |  |
| 8. MEDICAL EMERGENCY PROCEDURES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Call hospital ahead of time and give # of injured, Nature of injuries and names if the injured. Incidents requiring medevac – Transport to the airport near main building. Hay river hospital will send emergency team to the airport to transport injured to HR Hospital – They request a crew member travel to the hospital to aid in answering questions. Give them ENR contact number of 867-874-8225. Info requested by Hospital on injured personnel: - Date of birth - Home Address - Next of Kin - Heath Card Info |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 206 ICS 8/78 | 9. PREPARED BY Franco Nogarin |  |  |  |  |  |  |  |  |  | 10. REVIEWED BY John Ongo |  |  |  |  |  |  |  |

# Incident Org Chart

| # INCIDENT COMMUNICATIONS PLAN |  |  | 1. INCIDENT NAME |  |  | 2. DATE/TIME PREPARED | 3. OPERATIONAL PERIOD DATE/TIME |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Paradise Complex |  |  | July 20th, 2000 | July 21th, 0900-2100 |  |
| Paradise Branch |  |  |  |  |  |  |  |  |
| Assigned to | FUNCTION | CHANNEL |  | Simplex/Duplex | REMARKS |  |  |
| All Crews | Ground Ops | 5 |  | 153.47 |  |  |  |
| Ignition | Ignition Operations | 14 |  | 161.535 | All aircraft should monitor 122.05 am |  |  |
| Swampy Branch |  |  |  |  |  |  |  |
| Swampy Branch | Ground Operations | 10 |  |  |  |  |  |
| Swampy Branch | Air Operations | 9 |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |
| 5. PREPARED BY Franco Nogarin |  |  |  |  |  |  |  |  |

# HELICOPTERS

Paradise

CALL SIGN		TYPE			MAKE		PILOT		Medivac for

ZFN			Intermediate		AS350B2	Phil		Paradise

Swampy

JKN			Medium		205		Earl	 	Swampy

All Helicopters will continue to check in with XLI 55 for 30 minute check in

# MOB

| DATE | POSITION/TYPE | NAME | DESTINATION | TRANSPORT | Notes |
| --- | --- | --- | --- | --- | --- |

# NEW RESOURCE REQUEST

| RESOURCE NEED | DATE REQUIRED | DESTINATION | NOTES |
| --- | --- | --- | --- |

# OUTSTANDING ORDERS

| RESOURCE NEED | DATE REQUIRED | DATE REQUESTED | DESTINATION | NOTES |
| --- | --- | --- | --- | --- |

# DEMOB

| DATE | POSITION/TYPE | NAME | DESTINATION | TRANSPORT | Notes |
| --- | --- | --- | --- | --- | --- |
| July 23 | IC | Brent Starling | Fort Smith | FMD Truck | Dodge |
| July 23 | Plans | F. Nogarin | Fort Smith | FMD Truck |  |
| July 23 | Logs | Daniel Lund | Fort Simpson | Pers. Veh. |  |
| July 23 | Ass. Safety | Jordyn Siurko | Fort Res | ENR Truck |  |
| July 23 | FBAN | Dustin Oikle | YHZ | Sched | Flights need booking |
| July 23 | Ops | Edwin Gillis | YHZ | Sched | Flights need booking |
| July 23 | Safety | John Ongo | YHZ | Sched | Flights need booking |
| July 23 | Fin/Adm | Emily McInnis-Wharton | Fort Simpson | Pers. Veh. |  |
| July 22 | Div Sup | Manny Vital | Fort Liard | ENR Truck |  |
| July 21 | Crew | SS8 & SS10 | Fort Providence | Crew Truck | Pending Operations |

SWAMPY PARADISE COMPLEX (SS-037) CONTACT INFORMATION

INCIDENT MANAGEMENT TEAM

Position	Name	Phone Number

IC	Brent Starling	(867) 872-0486

Plans	Franco Nogarin	(867) 872-0393

FBAN	Dustin Oikle	(902) 956-4125

Div Sup	Manny Vital	(250) 321-0767

Ops	Edwin Gillis	(902) 432-2484

Swampy Branch Director	Lyle Froehlich	(867) 875-2504

Logistics	Daniel Lund	(867) 695-6676

Fin/Admin & Resource Unit	Emily McInnis-Wharton	(867) 444-8586

Fin/Admin & Time Unit	Raelene Lamalice	(867) 874-8225

Safety Officer	John Ongo	(902) 577-0930

Safety Officer	Jordyn Siurko	(867) 876-0601

Regional Office Duty Officer	Gerry Hordal	(867) 875-7443

District Area Office		(867) 875-5558

District Area Office Fire Clerk		(867) 875-5555

Incident Command Post	Raelene Lamalice	(867) 874-8225

Community Contacts

Mayor Andrew Cassidy	(867) 876-0528

Hay River Fire Chief, Ross Potter	(867) 876-0279

Hay River Ambulance Service	(867) 874-9333

Katl’odeeche First Nation Chief Roy Fabian	(867) 876-0079

Enterprise Mayor John Leskiw	(867) 984-3666

West Point First Nation	(867) 874-6677

Hay River Metis Council	(867) 874-4470

Dept. of Highways – Darin Murphy…………	(867) 875-7344

Dept. of Highways – Roy Norwegian	(867) 984-3421